## Sheet1 (2)
TC
Epic | Done | In Progress | Blocked | Planned | Non-Started
Manage Territory Capacities | 14 | 0 | 0 | 14 | 0 | 1
Manage patient details | 64 | 0 | 0 | 114 | 50
Capture Interactions | 26 | 4 | 0 | 76 | 46
Work with Scheduler | 74 | 0 | 0 | 112 | 38
Access Lightning Page | 5 | 0 | 0 | 5 | 0
Document time off and vacancy | 3 | 0 | 0 | 3 | 0
Total | 186 | 4 | 0 | 324 | 134
stories | [7 empty] | Epic | Done | Planned | Non-Started
Epic | Done | In Progress | Blocked | Planned | Non-Started |  |  | Manage Territory Capacities | 25 | 29 | 4 | 1 | 13 | 11
Manage Territory Capacities | 6 | 0 | 0 | 6 | 0 |  |  | Manage Initial Assignment | 45 | 74 | 29 | 45
Manage patient details | 13 | 0 | 0 | 15 | 2 |  |  | Manage Patient Details | 1 | 5 | 4 | 1
Capture Interactions | 9 | 4 | 0 | 18 | 5 |  |  | View History of New Patient | 0 | 0 | 0
Work with Scheduler | 16 | 0 | 0 | 19 | 3 |  |  | Document Time off and Vacancy | 105 | 120 | 15 | 56 | 49
Access Lightning Page | 3 | 0 | 0 | 3 | 0 |  |  | Set end User Access | 0 | 0 | 0
Document time off and vacancy | 2 | 0 | 0 | 2 | 0 |  |  | Total | 176 | 228 | 52
Total | 49 | 4 | 0 | 63 | 10
50
Testing phase | Passed | Failed | Blocked | Planned | Non-Started |  |  |  |  | 74
iEngage INT Release 6 | 80 | 1 | 0 | 104 | 23 |  | stories
Defects | Open | Done | Cancelled
Critical |  |  | 1
High | 1 | 3 |  |  | 3
Medium | 1 | 6 | 3 |  | 5
Low | 1 | 2 | 1 |  | 2 |  |  | Test automation | TCs | Not started
Total | 3 | 11 | 5 |  | 19 |  |  | iEngage Release 6 | 451 | #REF!
Non-Started
#REF!
.

## Sheet1
Overall Test case Execution summary :
Epic | No Run | Passed | Failed | In Progress | Blocked | Total
Territory Capacities | 0 | 46 |  |  |  | 46
Assignment | 0 | 99 |  |  |  | 99
Details | 0 | 15 |  |  |  | 15
History | 0 | 10 |  |  |  | 10
Vacancy | 0 | 80 |  |  | 1 | 81
Access | 0 | 20 | 1 |  |  | 21
Total | 0 | 270 | 1 | 0 | 1 | 272
Overall Defect Summary:
Epic | Canceled | Done | In Development | In Functional Testing | On Hold | Open | Ready For Functional Testing | Ready For Release | Reopened | Total
Territory Capacities | 1 | 2 |  | 1 | [5 empty] | 4
Assignment |  | 1 | [7 empty] | 1
Details | 1 | 1 | [7 empty] | 2
History |  | 1 | [7 empty] | 1
Vacancy |  | 0 | [7 empty] | 0
Access |  | 9 |  |  |  | 5 |  |  |  | 14
Total | 2 | 14 | 0 | 1 | 0 | 5 | 0 | 0 | 0 | 22